## Sheet1
Project Phase | Task Description | Owner | Status | Start Date | End Date | Deliverable / Output | GitHub File Path | Notes / Blockers
Data Access | Research and document API rate limits (Yahoo Finance, Alpha Vantage) | Ritika | In progress | 2025-09-24 | 2025-10-31 | API Access Plan
Database Design | Draft SQL schema for stocks, prices, features, predictions | Raisa | Planning | 2025-10-13 | 2025-10-31 | SQL Schema
Data Access | Implement data fetcher for batch ingestion | Ritika | Planning | 2025-10-15 | 2025-10-31 | src/batch_ingest.py
Database Design | Create ER diagram and link to Overleaf | Raisa | Planning | 2025-10-17 | 2025-10-19 | er_diagram.png
Documentation | Write Overleaf 3-page report | Ritika | Completed | 2025-10-26 | 2025-10-26
Modeling | Build baseline ML model for price prediction | Tarun | Planning | 2025-10-26 | 2025-11-02 | Model Training Notebook
Cloud Integration | BigQuery to SQL database | Ritika | Planning | 2025-10-29 | 2025-11-12 | ETL Cloud Pipeline
SQL Reports | Develop 8 analytical SQL queries and store results in Tableau/PowerBI | Tarun | Planning | 2025-11-03 | 2025-11-07 | SQL Reports
Submission | Submit GitHub + PDF + Tracker | All | Planning | 2025-12-03 | 2025-12-08 | Submission Confirmation
Validation | Verify GitHub repo + PDF + Excel completeness | All | Planning | 2025-12-03 | 2025-12-03 | Submission Package